Data Governance Overview

Update as of July 23, 2016

Prepared for

Utica National Insurance Group

Prepared by

Agile Insurance Analytics

Table of Contents

What is Data Governance and Why is it Important?	2

Utica National Data Governance Background	3

Recommendations for Utica Data Governance Program Initiation	4

Appendix A – Data Governance Charter Example	7

Appendix B – Sample Data Governance Operating Model	10

Utica National Insurance Group

Data Governance Overview

# What is Data Governance and Why is it Important?

Data Governance is a key data management building block for any organization that is seeking to use data as a competitive advantage and to become a data driven organization. The overall goal of data governance is to ensure the availability, usability, integrity, consistency, auditability, security, and compliance of the company’s data and associated processes. The major purpose of data governance is to help the organization reach its business objectives in a more efficient manner by maximizing the value and utility of its major corporate asset, data.

There are many additional reasons why organizations should initiate and employ data governance including:

- Compliance with regulations like SOX, HIPPA, Solvency II for auditability, traceability and lineage purposes;

- Putting into practice data management functions needed in order to align with new rating agency evaluation criteria;

- Improving use of its data and improving the quality of data on an enterprise basis;

- Ensuring that data being used for decision-making and external reporting and filing is accurate and timely;

- Provides the forum from an enterprise perspective for the sharing and enhancement of data

- Reduces the risks during business transformations and integration from M&A activity and company reorganizations.

- Provides a forum to assure that all major data decisions are being made in the best interests of the company.

Data Governance involves people working together to establish and enforce data policies/procedures, defining which data is subject to governance, and determining the allowable access and usage of such data to the appropriate organizational levels. The function also reviews and acts on requests for data access, data improvement initiatives, and data projects.  Data Governance is about people collaborating to establish a data/informational governance process that supports the needs of all business units and applicable external entities but with priority to enterprise goals and strategies.  It is the organization and implementation of policies, procedures, structure, roles and responsibilities which outline and enforce rules of engagement, decision rights, and accountabilities for the effective management of information assets.

Data Governance must be defined as a Business Program.

# Utica National Data Governance Background

In early 2014, Utica undertook the creation and implementation of an enterprise data governance program. This effort was seen as an important data management step in order to support the corporate data warehousing project that was in progress. This effort was an IT initiative led by Steve Alessendrini. The initiative’s objective was to get “their arms around” the internal data to be used to populate the corporate data warehouse being developed and to address the data quality problems being experienced with this data: Workers Comp and PPA data. The required data was also to be used to confirm and expand the OMG P&C data model being used by Utica. This initial Data Governance initiative was approved by the then CEO and CIO at Utica.

The initial Utica Data Governance organizational structure was a cross-functional committee, comprised of representatives from Marketing, Underwriting, Claims, Finance, Billing, Data Management, Personal Lines and IT. Plans were to expand the committee as needed as it matured. Business representatives were assigned data ownership of the data of which they had most control, e.g., Claims owned claims data, etc.  In addition, the role of Data Steward was identified and positioned under each applicable business/function.

Initial assignments were made providing data mapping templates to be used for developing “source to target” identifications as well as developing data names and data definitions. A sub-committee of the committee was established and charged with the development of data governance policies and procedures as well as defining the high level roles and responsibilities of the committee and its members. Work also commenced on the design and development of a Data Governance Work Bench to be used for accessing the “to be” developed metadata dictionary. The work that was assigned was in reality, data stewardship work.

A number of Data Governance meetings took place but as time went on interest and activity waned and time/resource limitations resulted in the effort being discontinued.

Interviews conducted by AIA with certain members of the previous Data Governance Committee suggested that such a data governance body would benefit the company and that the “targeted work” would have been beneficial but resources were not properly provided, that needed education on what data governance and data management did not take place, that the work assigned was overwhelming and that more structure was needed. Finally, lack of senior management support and involvement was cited as putting the final nail in this effort’s coffin.

Our assessment is that the direction of this initial data governance committee effort was proper and the efforts assigned and being undertaken were well thought out (starting out with a manageable target-WC and PPA). However, the weaknesses cited by the above interviewees were also “spot-on”. Senior management focus, proper resources/investment along with the needed structure/formality and education would have no doubt made this initial data governance effort more successful. However, a change in the leadership of this committee would have provided the message that the effort was a business effort and not an IT effort, as Data Governance needs to be driven by the business.  IT is neither the end user nor data expert of data use.  IT’s role is one of being a steward or custodian of data.

# Recommendations for Utica Data Governance Program Initiation

As mentioned, there are significant benefits that an organization can achieve with the implementation of a data governance program. Furthermore, there are economies of scale that can be achieved using an enterprise approach in the use of data facilitated by a data governance program that are not available in targeted or silo’d data efforts.

Leveraging the data governance work done in 2014 and in concert with the immediate plans to embrace an MDM solution for parties (customers, claimants, vendors, and agents), Utica can resurrect the data governance effort following the approach below.

- Obtain senior management commitment and involvement. Elicit corporate support for procuring the manpower and financial resources needed for managing and controlling data.

- Identify and recruit a change leader or data champion from the business side.

Criteria used by many organizations in choosing such a leader or chair of the data governance committee include:

- The individual’s use and knowledge of data in his/her operation and use of data organizationally.

- Appreciation of the need for quality data and the management of data as a corporate asset.

- Knowledge of the business and its objectives and strategies

- Possessing leadership characteristics and the ability to influence others.

- Having respect and collaboration with peers.

- Pull together a cross-functional steering committee to ensure that decisions and actions around data are consistent, standardized and create value across the enterprise. Insurance business users of data are now seeing the value of cross-functional enterprise data for running their respective operations. These committee members should be at least at a decision making level within their applicable departments and be able to represent their departments as well as understand the overall company goals and strategies. These individuals in effect become the “owner” of the data most used in their respective operation(s), eg., Claims will own claims data.

- Develop the structure and operating model/principles to be followed by the data governance committee. The Committee’s Charter, role and responsibilities, member roles and responsibilities, meeting guidelines, measurement of the effectiveness of data usage, etc., are to be formalized and communicated

Appendix A provides an example of a Data Governance Charter.

- Identify functional data stewards. Data stewards are charged with executing the direction given by the data governance committee. These individuals are business users who possess expert knowledge of business processes and how data is used within these processes. They create and maintain data definitions, metadata, ensure data quality, identify underlying causes of problems, initiate improvement efforts, and identify how business process changes and compliance issues impact data and its uses.

Appendix B shows an example of a data governance organization chart reflecting membership and supporting data stewards.

- The data governance committee, using input from all members, should develop an enterprise data strategy which outlines the data projects needed to address data challenges of the organization as well as use of data going forward.

Utica’s plans to implement a MDM requires that involvement of business data stewards , subject matter experts as part of the Data Governance structure be dedicated to aligning master data to business needs.

- Initiate, fund, oversee, and make decisions for a Party MDM initiative that aligns with the business strategy as the initial data governance project.  This entails oversight of these activities:

  - Assess the data quality and prioritize the data that should be addressed based on its importance to the organization

  - Inventory the MDM data; name and define this data;

  - Map source to target flows of this data;

  - Put into place data quality measures based upon the profiling effort for this data and assign the applicable data stewards to cleanse this flawed data.

  - Monitor the data quality clean-up effort

Note: a separate paper relating to a data quality program at Utica is being developed.

- Establish a communication plan that provides written status of the data governance committee’s improvement efforts and the benefits being achieved under this committee’s auspices. The developed data governance plan should also be communicated organizationally for all to access and see.

- Define and create Governance Relationships. The work and requirements of the data governance committee needs to be coordinated with the other organizational governance groups:

  - IT Governance for IT support, resources and tools including the need to acquire data management and BI/Analytic reporting technologies.

  - Corporate or Executive Management Governance on data strategies, project statuses and needed support and resources for data initiatives.

  - Information Security Committee input as to the impacts on data to systems and data management changes. This Committee should expand its scope to monitor and communicate compliance changes and pending regulatory changes that will effect data use within the organization.

- On-Going education is imperative for sustaining a viable Data Governance Committee and

# Appendix A – Data Governance Charter Example

Charter For

Utica National Insurance Group (UNIG)

Data Governance

SAMPLE for consideration

What is Data Governance?

Data Governance is the design, building, and operation of formal business processes and accountabilities to manage the enterprise data resource.  At Utica, Data Governance is an enterprise level function and program that involves all of our organizations and people.

Charter Statement

Data Governance (DG) is hereby formally chartered as the UNIG program ensure the availability, usability, integrity, consistency, auditability, security, and compliance of the company’s data and associated processes.

The DG Program is commissioned by the CEO and COO of UNIG and encompasses all of Utica and its subsidiaries.

The Data Governance Program has the accountability and authority to:

- Establish data governance guiding principles and policies

- Provide oversight for the acquisition, availability, usability, and quality of the data required by the business

- Make decisions about the data-intensive systems and tools to enable effective and efficient management and use of data

- Provide awareness, training, and education to all staff that have responsibilities for data management

- tbd

Oversight of the Data Governance Program is by the executive leadership team acting as the Data Governance Council.

Charter Detail

- Vision –  tbd

- Mission – tbd

We accomplish this Mission by attending to:

- Strategic Goals

  - tbd

  - tbd

- Scope

  - What is governed

    - All data in the UNIG domain

    - All core data management practice areas:

      - Tbd

      - Tbd

    - tbd

  - What is influenced

    - Data governance is part of everyone’s responsibility at UNIG

    - Coordination with legal, audit, security functions

    - Alignment of business and information strategies

    - tbd

  - What is communicated

    - Awareness and advocacy for data governance

    - Principles, Policies, and Practices for data governance

    - Data governance plans, activities, and accomplishments

    - Data governance training programs and opportunities

- Authority

  - Initiate data governance projects

  - Provide oversight of data management features other programs and projects

  - Formulate, promulgate, maintain, and enforce adherence to data-related principles and policies

  - Determine need for, and purchase of, tools that support data governance

  - Form/ disband work groups as needed

  - Train and appoint Data Stewards

  - Determine metrics for data governance success

  - Provide consultation for all data-related initiatives

  - Make decisions about referred questions and issues relevant to data governance

- Supporting Groups

  - Data Governance Council - this is a leadership team

  - Data Stewardship Teams – these are work groups that are coordination by a designated leader who communicates with the DG Council

- Alignment

  - Alignment to Utica strategies and goals

  - Legal and Compliance alliance to assure appropriate uses of data

  - Work with PMO on Data Governance projects

  - Data Stewards are aligned with data-intensive projects

Data Governance Operations

- This Charter establishes the strategic direction for Data Governance at Utica and defines the scope and the authority to operate.

- The Charter is to be reviewed and update annually.

- DG Council objectives and success criteria are established and metrics of performance are reported regularly.

- The DG Council meets at least monthly and adds special sessions as needed

- Leadership of the DG Council and Data Steward Program needs to be determined and could be rotated among the members of the group

- Data Governance publications (policies, etc.) are made available on the company’s website

- A Data Governance mailbox is available to anyone who has questions or would like more information:  tbd

The following sections may be added to the charter:

- Strategic Goals

- Critical Success Factors for Strategic Goals

- Tactical Objectives

  - Current Year

- Success Criteria for Tactical Objectives

  - Current Year

- Principles and Policies

- Publications

# Appendix B – Sample Data Governance Operating Model