| Process and Procedure Names: - Process: IT Management Operating System - Procedure: HUE within IT Waterfall/Agile Projects | Work Instruction Name: HUE (Honeywell User Experience) Planning | Effective Date: 20-Mar-2017 |
| --- | --- | --- |
| Work Instruction Owner: Tobias Komischke |  | Revision Date: 08-Dec-2017 |

# Purpose

Review project needs, integrate HUE (Honeywell User Experience) activities into the project plan and allocate HUE resources.

# Scope

# This work instruction is for planning HUE activities for a project.

# Work Instruction Activities

| Step # | Description | Owner (Role) | Details (e.g. screenshots, charts, etc.) |
| --- | --- | --- | --- |
|  | Meet with project manager and IT Business Partner/Business Analyst to review the nature of the project, incl. - Product or service offering / Project Type - New design or re-design (full or partial) - Pre-existing HUE knowledge, e.g. user feedback, user research, etc. - Available budget for HUE - Key HUE success criteria and ways to measure them, e.g. productivity gains, satisfaction, error prevention, etc. - Tentative timelines and milestones | HUE Representative | Examples for key HUE success criteria: - Key workflows can be executed 10% faster - System Usability Scale (SUS) score of 70 or higher Examples on how to measure: - Task completion time - SUS scale survey For project type definitions, refer to the Enterprise Procedure HUE document. |
|  | Integrate HUE activities in project plan: - Estimated start- and end-dates for each activity, aligned with other project activities | Project Manager | For HUE activities, refer to HUE Procedure document HUE Plan Template |
|  | Book HUE resources according to project plan: - Through IT HUE team (submit request through the Resource Request Form) and/or - Through 3rd party UX vendor and/or - Other staff trained in HUE | HUE Representative | Resource Request Form |
|  | Brief HUE resources on scope and nature of project; hand off to project manager for monitoring the execution part of the project; inform project sponsor as needed | HUE Representative |  |

# Enforcement

Failure to adhere to published policies, processes, procedures, work instructions and standards will be evaluated on a case by case basis and may result in disciplinary action.  Published policies, processes, procedures, work instructions and standards are also subject to audit by Honeywell Corporate Audit and external auditors for verification of compliance.

# Version Control and Review Frequency

# This Procedure is to be reviewed at minimum annually.

# Date Last Reviewed: 08-Dec-2017

Reviewed By: Tobias Komischke, IT HUE Leader

| Version # | Effective Date | Section(s) | Description | Author | Content/SME Approval | Work Instruction Owner Approval |
| --- | --- | --- | --- | --- | --- | --- |
| 1.0 | 20-Mar-2017 | Full document | First version | Tobias Komischke | Madhumita Gupta | Tobias Komischke |
| 1.1 | 25-Aug-2017 | “Work Instruction Activities” Section | Incoroporated reference to Project Types | Tobias Komischke | Madhumita Gupta | Tobias Komischke |
| 2.0 | 01-Nov-2017 | All | Incorporated new role of HUE representative and aligned to approved HUE process integration with waterfall/agile Software process | Madhumita Gupta | Tobias Komischke | Tobias Komischke |
| 2.1 | 08-Dec-2017 | All | Formatting edits based on Process Change Register requests | Tobias Komischke | Maadhu Gupta | Tobias Komischke |

*Process Owner, Process Governance and External Compliance approvals are through the automated tool